## User stories
USER STORIES
Theme | Priority | As the... | I want to be able to... | so I can...
UI | High | User | Login to the application | Use features of the application
UI | High | User | Logout of the application | End the current application session
UI | Low | User | Retrieve my password | Reset it if I forget my password
UI | High | User | Register a new profile | Login and use features of the application next time
UI | High | User | Manage my profile | View and edit my details and information
UI | High | User | Manage my schedule | View and edit my schedule
UI | Medium | User | View discussion forums | Scroll through the active discussions
UI | Medium | User | Post in discussion forums | Be an active part of discussions
UI | High | User | View other users profiles | Search for a user with simillar study interests
UI | Medium | User | Get help | Get generic help whenever needed
UI | Medium | User | Access all features through side nav bar | Navigate easily to all application options
UI | Medium | Developer | Provide good graphics | Enhance user experience
UI | High | User | Schedule a meeting | Setup a meeting when everyone is free
UI | High | User | Manage meetings | Change time/agenda or cancel meetings
UI | Medium | User | Receive application notifications | Receive reminders
UI | Low | User | Manage application notifications settings | Turn on/off notifications
UI | Medium | User | Start a discussion in the group | Have my doubts resolved quickly
UI | Medium | User | Comment on the discussion forums in the group | Help out others
UI | Low | User | receive reminders of the meeting | be on time for the meeting
UI | Medium | User | Block social media notifications | Focus on studying during meetings
UI | High | User | Manage groups | Search,join and leave groups
UI | High | Admin User | Manage people in the groups | Add/Remove people to the groups
Server | High | Developer | Setup the server connection | Make API calls between the front and back ends
Server | Low | User | Get e-mail alerts for meetings | Be up to date with my meeting schedules
Server | Low | User | Get sms alerts for meetings | Be up to date with my meeting schedules without any internet connection
Spike | High | Developer | Get aquainted with Android Development | Get a first hand experience on Android
Spike | High | Developer | Get well versed with SQLite | Setup & manage databases
Database | High | User | create a group | start forming a study group
Database | Medium | Admin User | add people to the group | have a larger study group
Database | Medium | Admin User | remove people from the group | remove people who aren't putting in their due share of effort
Database | Medium | User | join a group | start studying for that exam
Database | Medium | User | leave a group | leave a group which isn't working out for me
Database | High | User | search for groups | look for a one which matches my interest
Database | High | Developer | Setup the DB and the corresponding tables | Store data permanently on the application

## Product Backlog
PRODUCT BACKLOG
Theme | Item | Pts | Priority | Comments
General | Setting up the project folder | 4 | High | Needs to be done before actual features can be built
General | Test the connection between the front and back end | 2 | High
Spike | Get aquainted to android development | 4 | High
Spike | Get used to SQLite | 2 | High
Server | Setup the server connection and APIs | 4 | High
Database | Create the DB with tables as specified in design document | 4 | High
Database | Ensure proper relationship between the tables | 1 | High
UI | Login | 4 | High
UI | Logout | 4 | Low
UI | Retrieve password | 2 | Low
UI | Register | 8 | High
UI | Side bar navigation | 8 | Medium
UI | Homescreen layout | 2 | High
UI | Update my profile | 4 | Medium
UI | View my profile | 2 | Medium
UI | Create calendar template | 8 | Medium
UI | View my schedule | 2 | High
UI | Update my schedule | 8 | Medium
UI | View group schedule | 4 | High
UI | View other user profiles | 2 | Low
UI | Help | 1 | Low
UI | Schedule a meeting | 4 | High
UI | Cancel a meeting | 1 | Low
UI | Create a Meeting agenda | 2 | Medium
UI | Block social media notifications | 4 | Low
UI | Meeting reminders and notification | 4 | Low
UI | Notification settings | 2 | Low
UI | View discussions within the group | 2 | Medium
UI | Comment on the discussion within the group | 4 | Medium
UI | Join a group | 4 | High
UI | Search for a group | 2 | High
UI | Leave group | 2 | Low
UI | Add people to the group | 4 | High
UI | Remove people from the group | 2 | Low
UI | Scroll through public discussions | 2 | Low
General | Powerpoint presentation for sprint 1 | 2 | Medium
General | Powerpoint presentation for sprint 1 | 2 | Medium
General | Powerpoint presentation for sprint 1 | 2 | Medium
UI | Comment on public discussion thread | 4 | Low
General | Setting up GIT repositry | 1 | High
130

## Sprint 1
SPRINT BACKLOG | [5 empty] | Date | 3/14 - 3/20 |  |  | 3/21 - 3/27 |  |  | 3/28 - 4/3
Backlog Item | Pts. | Priority | Owner | Status | Remarks | Day: | W | F | M | W | F | M | W | F | M
Setting up the project folder | 4 | High | Akash
Test the connection between the front and back end | 2 | High | Shruti
Get aquainted to android development | 4 | High | Parikshit
Get used to SQLite | 2 | High | Shweta
Setup the server connection and APIs | 4 | High | Shashank
Create the DB with tables as specified in design document | 4 | High | Nikhil
Ensure proper relationship between the tables | 1 | High | Shweta
Login | 4 | High | Akash
Logout | 4 | High | Shashank
Register | 8 | High | Parikshit
Homescreen layout | 2 | High | Nikhil
Update my profile | 4 | High | Shruti
View my profile | 2 | Medium | Shruti
Setting up GIT repositry | 1 | High | Shashank
46
Note on B2: Based on complexity. Initial estimate should follow: exponential (1,2,4,8,...) OR fibonacci (1,2,3,5,8,...)
Note on C2: How important is this?
Note on D2: Who gets choked if this item doesn't get done?
Note on E2: Done? Blocked? Choose an item from the drop-down menu.
Note on B3: Based on complexity. Initial estimate should follow: exponential (1,2,4,8,...) OR fibonacci (1,2,3,5,8,...)
Note on C3: How important is this?
Note on D3: Who gets choked if this item doesn't get done?
Note on E3: Done? Blocked? Choose an item from the drop-down menu.

## Sprint 1 Burndown
Sprint 1 Burndown Chart
Date | 3/14 - 3/20 |  |  | 3/21 - 3/27 |  |  | 3/28 - 4/3
Day | W | F | M | W | F | M | W | F | M
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Actual | 0 | 37 | 37 | 37 | 37 | 35 | 33.5 | 30.5 | 15
Ideal | 39 | 32.375 | 27.75 | 23.125 | 18.5 | 13.875 | 9.25 | 4.625 | 0