## User stories
USER STORIES
Theme | Priority | As the... | I want to be able to... | so I can...
UI | High | User | Login to the application | Use features of the application
UI | Low | User | Logout of the application | End the current application session
UI | Low | User | Retrieve my password | Reset it if I forget my password
UI | High | User | Register a new profile | Login and use features of the application next time
UI | Medium | User | Manage my profile | View and edit my details and information
UI | High | User | Manage my schedule | View and edit my schedule
UI | Medium | User | View discussion forums | Scroll through the active discussions
UI | Medium | User | Post in discussion forums | Be an active part of discussions
UI | High | User | View other users profiles | Search for a user with simillar study interests
UI | Low | User | Get help | Get generic help whenever needed
UI | Medium | User | Access all features through side nav bar | Navigate easily to all application options
UI | High | User | Schedule a meeting | Setup a meeting when everyone is free
UI | High | User | Manage meetings | Change time/agenda or cancel meetings
UI | Medium | User | Receive application notifications | Receive reminders
UI | Low | User | Manage application notifications settings | Turn on/off notifications
UI | Medium | User | Start a discussion in the group | Have my doubts resolved quickly
UI | Medium | User | Comment on the discussion forums in the group | Help out others
UI | Low | User | receive reminders of the meeting | be on time for the meeting
UI | Medium | User | Block social media notifications | Focus on studying during meetings
UI | High | User | Manage groups | Search,join and leave groups
UI | High | Admin User | Manage people in the groups | Add/Remove people to the groups
Server | High | Developer | Setup the server connection | Make API calls between the front and back ends
Spike | High | Developer | Get aquainted with Android Development | Get a first hand experience on Android
Spike | High | Developer | Get well versed with SQLite | Setup & manage databases
Database | High | Developer | Setup the DB and the corresponding tables | Store data permanently on the application

## Product Backlog
PRODUCT BACKLOG
Theme | Item | Pts | Priority | Comments
General | Setting up the development environment | 4 | High | Needs to be done before actual features can be built
General | Test the connection between the front and back end | 2 | High
Spike | Get aquainted to android development | 8 | High
Spike | Get used to SQLite queries | 4 | High
Server | Setup the server connection and APIs | 4 | High
Database | Create the DB with tables as specified in design document | 4 | High
Database | Ensure proper relationship between the tables | 1 | High
UI | Login | 4 | High
UI | Logout | 4 | Low
UI | Retrieve password | 2 | Low
UI | Register | 8 | High
UI | Side bar navigation | 8 | Medium
UI | Homescreen layout | 2 | High
UI | Update my profile | 4 | Medium
UI | View my profile | 2 | Medium
UI | Create calendar template | 8 | Medium
UI | View my schedule | 4 | High
UI | Update my schedule | 4 | Medium
UI | View group schedule | 4 | High
UI | View other user profiles | 2 | Low
UI | Help | 1 | Low
UI | Schedule a meeting | 4 | High
UI | Cancel a meeting | 1 | Low
UI | Create a Meeting agenda | 2 | Medium
UI | Block social media notifications | 4 | Low
UI | Meeting reminders and notification | 4 | Low
UI | Notification settings | 2 | Low
UI | View discussions within the group | 2 | Medium
UI | Comment on the discussion within the group | 4 | Medium
UI | Join a group | 4 | High
UI | Search for a group | 2 | High
UI | Leave group | 2 | Low
UI | Add people to the group | 4 | High
UI | Remove people from the group | 2 | Low
UI | Scroll through public discussions | 2 | Low
General | Powerpoint presentation for sprint 1 | 2 | High
General | Powerpoint presentation for sprint 2 | 2 | High
General | Powerpoint presentation for sprint 3 | 2 | High
UI | Comment on public discussion thread | 4 | Low
General | Setting up GIT repositry | 1 | High

## Sprint 1
SPRINT BACKLOG | [5 empty] | Date | 9/23 - 9/29 |  |  | 9/30 - 10/6 |  |  | 10/7 - 10/13
Backlog Item | Pts. | Priority | Owner | Status | Remarks | Day: | W | F | M | W | F | M | W | F | M
Setting up the development environment | 2 | High | Akash |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Test the connection between the front and back end | 2 | High | Parikshit |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Get aquainted to android development | 8 | High | All |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Get used to SQLite queries | 4 | High | Shweta |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Setup the server connection and APIs | 4 | High | Shashank |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Create the DB with tables as specified in design document | 4 | High | Akash |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Ensure proper relationship between the tables | 1 | High | Shweta |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Login | 4 | High | Nikhil |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Logout | 4 | Low | Shashank |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Register | 8 | High | Parikshit |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Homescreen layout | 2 | High | Nikhil |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Update my profile | 4 | Medium | Shruti |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
View my profile | 4 | Medium | Shruti |  |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Setting up GIT repositry | 1 | High | Shashank |  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Powerpoint presentation for sprint 1 | 2 | High | Shweta |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Note on B2: Based on complexity. Initial estimate should follow: exponential (1,2,4,8,...) OR fibonacci (1,2,3,5,8,...)
Note on C2: How important is this?
Note on D2: Who gets choked if this item doesn't get done?
Note on E2: Done? Blocked? Choose an item from the drop-down menu.

## Sprint 1 Burndown
Sprint 1 Burndown Chart
Date | [week 1] |  |  | [week 2] |  |  | [week 2]
Day | W | F | M | W | F | M | W | F | M
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Actual | 54 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53
Ideal | 54 | 47.25 | 40.5 | 33.75 | 27 | 20.25 | 13.5 | 6.75 | 0